## Sheet1
Project Deliverables - 77 Hrs
Project Management - 5 Hrs | Kanboard - 2.5 Hrs | HTML - 12 Hrs | CSS - 12 Hrs | Documentation - 15 Hrs | Testing - 3 Hrs | Team Meetings - 9 Hrs | Website Design - 7 Hrs | Project Release - 8 Hrs | Product Owner meetings - 2 Hrs | Lessons learned - 1.5 Hrs
Week4 Oct05 0.5 hours | Week4 Oct05 0.25 hours | Feature HTML CODE - 1 1 hour | CSS Feature 1 1 hour | Preliminary Project Ideas 3 hours | Testing Feature 1 0.25 hours | Team Meetings 1 1 hour | Website Design Diagram 0.5 hours | Deployment Sprint1 0.5 hours | Meeting1 0.5 hours | Report 1 0.5 hours
Week5 Oct12 0.5 hours | Week5 Oct12 0.25 hours | Feature HTML CODE - 2 1 hour | CSS Feature 2 1 hour | Team SWOT Analysis 1 hours | Testing Feature 2 0.25 hours | Team Meetings 2 1 hour | Figma Website Look diagram 0.5 hours | Deployment Sprint2 0.5 hours | Meeting2 0.5 hours | Report 2 0.5 hours
Week6 Oct19 0.5 hours | Week6 Oct19 0.25 hours | Feature HTML CODE - 3 1 hour | CSS Feature 3 1 hour | Project Approval Request Form 1 hours | Testing Feature 3 0.25 hours | Team Meetings 3 1 hour | Design Feature 1 - 0.5 hours | Deployment Sprint3 0.5 hours | Meeting3 0.5 hours | Report 3 0.5 hours
Week7 Oct31 0.5 hours | Week7 Oct31 0.25 hours | Feature HTML CODE - 4 1 hour | CSS Feature 4 1 hour | Team Organisation Chart 1 hours | Testing Feature4 0.25 hours | Team Meetings 4 1 hour | Design Feature 2 - 0.5 hours | Deployment Sprint4 0.5 hours | Meeting4 0.5 hours
Week8 Nov02 Reading Break 0.5 hours | Week8 Nov02 Reading Break 0.25 hours | Feature HTML CODE - 5 1 hour | CSS Feature 5 1 hour | Project Feature priority Chart 0.5 hours | Testing Feature 5 0.25 hours | Team Meetings 5 1 hour | Design Feature 3 - 0.5 hours | Week12 Nov24 Presentation 3 hours
Week9 Nov09 0.5 hours | Week9 Nov10 0.25 hours | Feature HTML CODE - 6 1 hour | CSS Feature 6 1 hour | Project Charter 2.5 hours | Testing Feature 6 0.25 hours | Team Meetings 6 1 hour | Design Feature 4 - 0.5 hours | Week13 Dec01 Presentation 3 hours
Week10 Nov16 0.5 hours | Week10 Nov17 0.25 hours | Feature HTML CODE - 7 1 hour | CSS Feature 7 1 hour | Deliverables schedule 1 hour | Testing Feature 7 0.25 hours | Team Meetings 7 1 hour | Design Feature 5 - 0.5 hours
Week11 Nov23 0.5 hours | Week11 Nov24 0.25 hours | Feature HTML CODE - 8 1 hour | CSS Feature 8 1 hour | Project WBS chart 2 hours | Testing Feature 8 0.25 hours | Team Meetings 8 1 hour | Design Feature 6 - 0.5 hours
Week12 Nov24 0.5 hours | Week12 Nov25 0.25 hours | Feature HTML CODE - 9 1 hour | CSS Feature 9 1 hour | Documention Feature 1 0.25 hours | Testing Feature 9 0.25 hours | Team Meetings 9 1 hour | Design Feature 7 - 0.5 hours
Week13 Dec01 0.5 hours | Week13 Dec02 0.25 hours | Feature HTML CODE - 10 1 hour | CSS Feature 10 1 hour | Documention Feature 2 0.25 hours | Testing Feature 10 0.25 hours |  | Design Feature 18 - 0.5 hours
|  | Feature HTML CODE - 11 1 hour | CSS Feature 11 1 hour | Documention Feature 3 0.25 hours | Testing Feature 11 0.25 hours |  | Design Feature 9 - 0.5 hours
|  | Feature HTML CODE - 12 1 hour | CSS Feature 12 1 hour | Documention Feature 4 0.25 hours | Testing Feature 12 0.25 hours |  | Design Feature 10 - 0.5 hours
|  |  |  | Documention Feature 5 0.25 hours |  |  | Design Feature 11 - 0.5 hours
|  |  |  | Documention Feature 6 0.25 hours |  |  | Design Feature 12 - 0.5 hours
Documention Feature 7 0.25 hours
Documention Feature 8 0.25 hours
Documention Feature 9 0.25 hours
Documention Feature 10 0.25 hours
Documention Feature 11 0.25 hours
Documention Feature 12 0.25 hours